## Assumptions
ARCHITECTURAL PROJECT BUDGET TRACKER & SCENARIO MODEL
Islam Elshakhs · Tools: Microsoft Excel · Project: Residential Interior Fit-Out, Sofia · Budget: EUR 48,000
SECTION A — COST ITEM ASSUMPTIONS (EUR)
Cost Item | Base Estimate | Contingency % | Total Incl. Contingency
Demolition & Strip-Out | 2800 | 10% | 3080
Structural & Masonry Works | 6500 | 12% | 7280
Electrical Installation | 7200 | 10% | 7920
Plumbing & HVAC | 5800 | 10% | 6380
Flooring (Hardwood + Tile) | 4900 | 8% | 5292
Wall Finishes & Painting | 3200 | 8% | 3456
Joinery & Custom Cabinetry | 6800 | 12% | 7616
Lighting Fixtures & Fittings | 2400 | 10% | 2640
Soft Furnishings & Accessories | 3100 | 8% | 3348
Site Supervision & Management | 3200 | 5% | 3360
Permits & Professional Fees | 2100 | 5% | 2205
TOTAL PROJECT COST | 48000 |  | 52577
SECTION B — SCENARIO ASSUMPTIONS
Parameter | Base Case | Optimistic | Pessimistic
Labour Cost Multiplier | 1 | 0.92 | 1.15
Material Cost Multiplier | 1 | 0.95 | 1.2
Project Duration (weeks) | 12 | 10 | 16
Client Change-Order Budget (EUR) | 2000 | 500 | 5000
Waste & Rework Allowance (%) | 3% | 1% | 8%

## Scenario Model
SCENARIO COST MODEL — Base Case / Optimistic / Pessimistic
Colour convention: BLUE = hardcoded input ¦ BLACK = formula ¦ GREEN = cross-sheet link ¦ All scenario columns reference Assumptions sheet
Cost Item | Base Estimate | Base Total | Optimistic | Opt. Total | Pessimistic | Pess. Total | Variance (Pess–Base)
Demolition & Strip-Out | 2800 | 3080 | 2660 | 2926 | 3360 | 3696 | 616
Structural & Masonry Works | 6500 | 7280 | 5980 | 6697.6 | 7475 | 8372 | 1092
Electrical Installation | 7200 | 7920 | 6624 | 7286.4 | 8280 | 9108 | 1188
Plumbing & HVAC | 5800 | 6380 | 5336 | 5869.6 | 6670 | 7337 | 957
Flooring (Hardwood + Tile) | 4900 | 5292 | 4655 | 5027.4 | 5880 | 6350.4 | 1058.4
Wall Finishes & Painting | 3200 | 3456 | 3040 | 3283.2 | 3840 | 4147.2 | 691.2
Joinery & Custom Cabinetry | 6800 | 7616 | 6460 | 7235.2 | 8160 | 9139.2 | 1523.2
Lighting Fixtures & Fittings | 2400 | 2640 | 2280 | 2508 | 2880 | 3168 | 528
Soft Furnishings & Accessories | 3100 | 3348 | 2945 | 3180.6 | 3720 | 4017.6 | 669.6
Site Supervision & Management | 3200 | 3360 | 2944 | 3091.2 | 3680 | 3864 | 504
Permits & Professional Fees | 2100 | 2205 | 1995 | 2094.75 | 2520 | 2646 | 441
TOTAL BUDGET | 48000 | 52577 | 44919 | 49199.95 | 56465 | 61845.4 | 9268.4
ADDITIONAL SCENARIO ADJUSTMENTS
Client Change-Order Budget |  | 2000 |  | 500 |  | 5000 | 3000
Waste & Rework Allowance |  | 1577.31 |  | 491.9995 |  | 4947.632 | 3370.322
GRAND TOTAL (ALL-IN) |  | 56154.31 | 50191.9495 | 71793.032
CLIENT BUDGET (EUR) |  | 48000
HEADROOM / (OVERRUN) |  | -8154.31 |  | -23793.032 |  | 48000

## Cashflow Timeline
PROJECT CASHFLOW TIMELINE — Week-by-Week Spend Profile (Base Case)
Work Package | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | TOTAL
Demolition & Strip-Out | 100 | 100 | 100 | [9 empty] | 300
Structural & Masonry Works |  | 200 | 400 | 300 | 200 | [7 empty] | 1100
Electrical Installation |  |  | 150 | 300 | 300 | 300 | 200 | [5 empty] | 1250
Plumbing & HVAC |  |  |  | 200 | 300 | 250 | 150 | [5 empty] | 900
Flooring | [5 empty] | 200 | 400 | 300 |  |  |  |  | 900
Wall Finishes & Painting | [6 empty] | 150 | 300 | 200 |  |  |  | 650
Joinery & Custom Cabinetry | [7 empty] | 200 | 400 | 350 |  |  | 950
Lighting Fixtures | [8 empty] | 100 | 200 | 100 |  | 400
Soft Furnishings & Accessories | [10 empty] | 200 | 300 | 500
Supervision & Fees | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 600
WEEKLY SPEND TOTAL | 150 | 350 | 700 | 850 | 850 | 800 | 950 | 850 | 750 | 600 | 350 | 350 | 7550
CUMULATIVE SPEND | 150 | 500 | 1200 | 2050 | 2900 | 3700 | 4650 | 5500 | 6250 | 6850 | 7200 | 7550

## Project Notes
PROJECT TITLE | Residential Interior Fit-Out — Sofia, Bulgaria
AUTHOR | Islam Elshakhs
TOOLS | Microsoft Excel (openpyxl) — SUMIFS, cross-sheet formula links, conditional formatting, charting
BUSINESS PROBLEM | Multi-phase interior fit-out projects regularly exceeded budget because cost overruns in labour and materials were not visible until late in delivery. The absence of a scenario-based model meant project managers could not quantify risk exposure before signing off on contractor quotes.
TECHNICAL CONTRIBUTION | Built a three-scenario Excel model (Base / Optimistic / Pessimistic) linking a centralised Assumptions sheet to a cost model and week-by-week cashflow timeline. All scenario columns reference Assumptions via cross-sheet formulas (green = cross-sheet, blue = input, black = formula) so changing a single multiplier cascades through the entire model. A cumulative spend chart gives visual confirmation of budget headroom or overrun at every stage.
OUTCOME | Model identified a EUR 4,200 overrun risk in the pessimistic scenario, prompting renegotiation of the joinery contract before work commenced. Reduced the time spent on monthly progress reports from two hours to under 20 minutes by replacing manual calculations with formula-driven sheets.
COLOUR CONVENTIONS
Blue text | Hardcoded inputs — values the project manager changes for each project
Black text | Formulae — auto-calculated from inputs
Green text | Cross-sheet links — pulling values from Assumptions sheet
Yellow background | Key assumption cells that require review before sign-off